## ALL Phase
| Deploy Proxmox Private Cloud Timeline Yutaka Manufacturing |  |  |  |  | Project start: | [7 empty] | 2026-02-01
[6 empty] | Display week: | [7 empty] | 1
Project lead
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5
| Timeline description | Assigned to | Progress | Start | Days | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08
[6 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule. | Preparation
Preparation
| Preparation Networking Design | CBNCloud and Customer | 0% |  | 2.5 | bar: M to W
| Prepare Baremetal Server | CBNCloud and Customer | 0% |  | 2.5 | bar: W to F
Deployment Proxmox New Server
| Setup Node Server on Rack | CBNCloud and Customer | 0% |  | 1.5 | bar: M to T
| Setup Network Node to Cluster and Storage Server | CBNCloud and Customer | 0% |  | 1 | bar: T to W
| Configure Network Cluster and Storage Server | CBNCloud and Customer | 0% |  | 0.5 | bar: W to T
| Install Proxmox | CBNCloud | 0% |  | 0.2 | bar: T
| Update and Config Cluster Proxmox | CBNCloud | 0% |  | 0.2 | bar: T
Migration VM from VMware Server 1 to Proxmox New Server
| Setup Connection from VMware Server 1 to Proxmox New Server | CBNCloud & Customer | 0% |  | 0.25 | bar: F
| Attach ESXI to Proxmox dashboard | CBNCloud & Customer | 0% |  | 0.25 | bar: F
| Start Migration | CBNCloud | 0% |  | 2 | bar: F to S
| Start the VM and Reconfig IP | CBNCloud | 0% |  | 0.25 | bar: S
| Verify Data | CBNCloud & Customer | 0% |  | 0.25 | bar: S
Migration VM from VMware Server 2 to Proxmox New Server
| Setup Connection from VMware Server 2 to Proxmox New Server | CBNCloud & Customer | 0% |  | 0.25 | bar: M
| Attach ESXI to Proxmox dashboard | CBNCloud & Customer | 0% |  | 0.25 | bar: M
| Start Migration | CBNCloud | 0% |  | 1.5 | bar: M to W
| Start the VM and Reconfig IP | CBNCloud | 0% |  | 0.5 | bar: W
| Verify Data | CBNCloud & Customer | 0% |  | 0.5 | bar: W
Testing
| Test Connectivity each Nodes | CBNCloud | 0% |  | 0.2 | bar: T
| Test Create VM | CBNCloud | 0% |  | 0.2 | bar: T
| Test VM Migration to another node | CBNCloud | 0% |  | 0.2 | bar: T
Monitoring and UAT
| UAT to Customer | CBNCloud & Customer | 0% |  | 3 | bar: T to S
| Total |  |  |  | 18
Note : Bandwidth 1G
Re-build for VM AD by user